## Billing Additional Tasks
User | Task | Time Spent on Task | Progress | Date Start | Date Finish
Morty | Work with UPSer to get comfortable with sql | 1.5 Hours | 100% | 2019-11-20 | 2019-11-20
Brandon | Issues DB Weekly Review Form | 3hrs | 100% | 2019-10-15 | 2019-10-21
Nick & Morty | Ensure those that need SQL Server admin rights have it. | 30min | 100% | 2019-10-11 | 2019-10-15
Morty | Analyze process improvement | 10 hours | 100%
Nick | ISPS Monthly DB Table Migration: ISPSUsers | 2 hours | 100% | 2019-10-28 | 2019-10-28
Sophia | ISPS Monthly DB Table Migration: FinalPurgeList | 30min | 100% | 2019-10-31 | 2019-10-31
Jeff | ISPS Monthly DB Table Migration: DataSecFile | 30min | 100% | 2019-10-28 | 2019-11-01
Nick | ISPS table migration assistance | 2hr | 100% | 2019-10-28 | 2019-10-31
Sophia | Generate Purge List Query | 30min | 100% | 2019-10-28 | 2019-11-04
Sophia | Generate Purge Text Files Query | 10min | 100% | 2019-10-28 | 2019-11-04
Jeff | Generate Comm Spec Query | 10min | 100% | 2019-11-22 | 2019-11-22
Jeff | Generate Data Security File Query | 10min | 100% | 2019-11-22 | 2019-11-22
Nick | Generate Duplicate Employee ID List Query | 30min | 100% | 2019-11-04 | 2019-11-04
Tau & Dom & Nick | Change Last Sign on to Date Query | 10 min | 100% | 2019-11-01 | 2019-11-01
Dom & Tau & Nick | Change Last Updated By to Date Query | 10min | 100% | 2019-11-01 | 2019-11-01
Nick | ISPS Monthly DB Query Migration assistance | 30min | 100% | 2019-11-04 | 2019-11-04
Morty | Assist in finding AE in DWH to shorten co-UPSers Paper project manual search time | 45min | 100% | 2019-11-07 | 2019-11-07
Morty | Demonstrate SQL 101 | 1 hour | 100% | 2019-11-06 | 2019-11-06
Nick | Update naming convention on table column names / update query names to match | 30min | 100% | 2019-11-11 | 11//19
Nick | Migrate print vendor data to SQL S. | 1.5 hours | 100% | 2019-11-12 | 2019-11-12
Sophia | Issues Form Mockup | 1 hour | 100% | 2019-11-05 | 2019-11-05
Sophia | Interim Form Mockup | 1 hour | 100% | 2019-11-20 | 2019-11-20
Sophia | SQL Training | 1 hour | 100% | 2019-11-13 | 2019-11-13
Brandon/Tau/Morty/Jeff | UAD Audit Database - Flow Chart Analysis | 1 hour | 100% | 2019-11-26
Nick | Create C# program to automate loading of Print Vendor data to SQL S. | 2 hours | 100% | 2019-11-15 | 2019-12-01
Mike Fig, Pawel, Dom | Interim Database - Back End | 10 hours | 80% | 2019-12-04
Mike Fig, Pawel, Dom | Interim Database - Front End | 4 hours | 75% | 2019-11-21
Mike | Add Purge Flag Query
Brandon/Tau/Morty/Jeff/Ellen | UAD Audit Database - Front End | 1 hour |  | 2019-11-11
Brandon/Tau/Morty/Jeff/Ellen | UAD Audit Database - Back End | 3 hours |  | 2019-12-12
Brandon | ISPS Monthly Task Database | 2 hours |  | 2019-11-11
Tau/Pawel/Brandon | Error File Database Migration | 1 hour |  | 2019-12-06
Mike Fig | Interim Database - Coding | 12 Hours |  | 2019-12-11
Morty | DWH query for paper project | 2 hours | 100% | 2019-12-01 | 2019-12-07
Brandon | Exception Error Database | 7 hours | 85% | 2019-12-13
Brandon | Organization and Expansion training | 1 hour | 60% | 2019-12-20
Dom | Cleaning up Tables & Queries pages in OneNote | 1 hour | 100% | 2019-12-22 | 2019-12-22
Morty | Ssis 101 | 1 hour 10 mins | 100% | 2019-12-26 | 2019-12-26
Dom | Transfer Interim Database Info From OneNote to Github (formatting & organizing) | 2 Hours | 70% | 2019-12-27
Dom | Transfer Billing Additional Tasks Table to GitHub Wiki | 1 Hour | 10% | 2019-12-27
Dom | Learn Markdown Format Language for Github Wiki | 30 mins | 100% | 2019-12-27 | 2019-12-27
Morty and 'Mike' | Create test environment for both the EDI and billing DBs | 1 hour 45 mins | 100% | 2020-02-13 | 2020-02-13
Morty | Demonstrate proper code commenting standards | 1 hour | 100% | 2020-02-06 | 2020-02-06
Morty | Comment the code put in already | 3 hours | Ongoing | 2020-02-06
Morty | Demonstrate how to import file securely via c# | 45 mins | 100% | 2020-02-10 | 2020-02-10
Morty | Review Comments of code submitted by users | 30 mins | Ongoing | 2020-02-13
Paul | Comment the code already in use | 2 hours | Ongoing | 2020-02-12
Mike Fig | Code comments | 8 hours | Ongoing | 2020-02-12
Dom | Code comments | 3 hours | Ongoing | 2020-02-18